## Screening
Portfolio Screening
Four methods ranked side-by-side. rank_spread = max(rank) − min(rank); high spread = scoring-sensitive idea, dig deeper.
Idea | Mod. RICE | WSJF | CD3 ($/yr) | EMV ($) | R(RICE) | R(WSJF) | R(CD3) | R(EMV) | Rank spread | Avg rank
Patent licensing (yield model) | 38.4 | 114.6 | 960000 | 3760000 | 1 | 2 | 2 | 1 | 1 | 1.5
WhatsApp pest-alert bot | 22.05 | 432.0222 | 980000 | 401000 | 2 | 1 | 1 | 3 | 2 | 1.75
AgriSense advisory | 5.3333 | 76.6667 | 666666.6667 | 3600000 | 3 | 3 | 3 | 2 | 1 | 2.75
FPO marketplace | 0.46286 | 57.7 | 270000 | 380000 | 4 | 4 | 4 | 4 | 0 | 4
Soil-sensor hardware | 0.26667 | 28.96 | 96000 | 300000 | 5 | 5 | 5 | 5 | 0 | 5

## Definitions
Method Definitions
Term | Definition | When to trust this method
Reach (RICE) | How many customers a project will impact. | Captured as Monetary impact × Adoption fraction.
Impact (RICE) | How much a project shifts a strategic goal. | Captured as Business-critical × Ownership.
Confidence (RICE) | How sure we are in the estimates. | Captured as Risk PoS × Time of replacement.
Effort (RICE) | Total time and money required. | Captured as Time to commercialize × Cost to develop.
Modified RICE | Samyama variant: (Reach × Impact × Confidence) / Effort. | Quick portfolio-level screen — higher is better.
WSJF | Weighted Shortest Job First (SAFe): (Business Value + Time Criticality + Risk Reduction) / Duration. | Use when you care about delivery sequencing and time-to-market.
CD3 | Cost of Delay ÷ Duration (Reinertsen). | Use when you can estimate $/year lost by delaying the project.
EMV | Expected Monetary Value: PoS × (annual value × life) − cost. | Use when comparing projects in dollars rather than scores.